## Hoja 1
Subject | Description | Accepted | Conclusion
Schedule | Try to define a time schedule for the technical demo | Pending |  |  | Talking points:
Technical Demo | Define and specify the components of the technical demo | Accepted |  |  | Introduction and revision over current information
Environment sketch | Draw al teast one sketch of the different technical demo's scenes | Accepted |  |  | <-
Environment Graphics | List all the enviromental graphics used in the technical demo, for instance: house floor, house door, walls, cauldron, etc. | Accepted | Defined but pending Illustrator
Character attibutes | List and specify all the characters attibutes, like stregth, speed, magic, etc. | Accepted | Defined in Game Design Doc
Battle system | Specify the battle system components, turns, rules, etc. | Accepted | Defined in Game Design Doc
Story compatiblity | Describe the story to the participants from the webcomic side of things to make sure that the current story progression is kept as compatible with the webcomic as possible. | Accepted | Everything is compatible.
Artist recruitment | Decide how to go about finding a replacement for Zoltan and wether or not we can get help from the existing community. | Accepted | Contact page for David to public in social media
Further discuss Asra | Asra is the main antagonist, we should discuss certain aspects of her to make sure it's not too dark. | Accepted | Everything is compatible.
Team members | Make a list with all the team members, including his/her contact email, role in the project and previous experience (if any). | Accepted | Done
Types of character | Discuss the RPG character | Accepted | Shichimi: Slow and powerful, magical healer | Coriander: Tanky, heals physical damage. May fight with physical attacks. | Saffron: Quick attacks, cheap magic but not so powerfull | Pepper: Self damage or partners, lots of power. Complex magic, hard to spell but very powerfull
Map |  | Accepted | Map should not contain the physical location of the worlds